EE6008 Collaborative Research and Development Project

Project Charter

<<AY26S1-14-SPML Human Pose Analytics Using Artificial Intelligence>>

Students’ Names: <<Kolmakov Kirill, Liang Hanzhang, Teng Ziying, Shen Cong, Zhao Zhenning>>

Supervisor’s Name: <<Yap Kim Hui>>

School of Electrical and Electronic Engineering

Academic Year 2026/27

Semester 1

| Date Prepared: | 26 August 2026 |
| --- | --- |

| Project No. & Project Title | AY26S1-14-SPML Human Pose Analytics Using Artificial Intelligence |
| --- | --- |
| Project Supervisor | Yap Kim Hui |
| Team Leader | Liang Hanzhang |
| Names of Team Members | Kolmakov Kirill, Teng Ziying, Shen Cong, Zhao Zhenning |

Project Purpose or Justification:

Multi-person interaction recognition plays a vital role in video-based human motion understanding and pose analytics. Although deep-learning methods have achieved high accuracy in skeleton-based action recognition, many current approaches rely on early joint heatmap fusion or spatial aggregation across multiple individuals. This often leads to the loss of individual person identity and relative geometric dynamics, making it difficult for models to accurately distinguish role-asymmetrical and interactive actions. To address this limitation, this project aims to develop an instance-preserving pose representation for multi-person action recognition without significantly increasing backbone complexity. By explicitly retaining individual person identities alongside relative displacement, distance, and velocity cues, the proposed framework aims to enhance fine-grained multi-person interaction analysis.

Project Description:

This project focuses on multi-person identity preservation in human pose and motion analysis, aiming to maintain consistent individual identities across frames for reliable downstream motion analysis. · Technical Direction and Baseline: Select datasets, representations, and downstream models for the confirmed direction — primarily the two-person interaction subset of NTU RGB+D 120 — and establish a reproducible baseline pipeline from skeleton input to action recognition, together with appropriate evaluation metrics. · Research Innovation: Following mentor confirmation, the project focuses on multi-person identity preservation for interaction action recognition. Existing skeleton-based methods either fuse multiple persons into a shared heatmap or average per-person features, so instance identity and inter-person geometry are never modelled explicitly. From Week 6 onward, our team will develop an instance-preserving pose representation and evaluate whether it improves recognition of two-person interactions. · Evaluation & Testing: Evaluate the baseline and the proposed method under identical settings. Experiments will cover top-1 accuracy and macro-F1 on the interaction subset, per-class results on role-asymmetric classes, sensitivity to person-index swapping, ablations that isolate the contribution of identity preservation from added parameters, and computational cost.

| Summary Milestones | Target Date |
| --- | --- |
| • Complete initial literature review on human pose analytics; acquire fundamental knowledge from several key papers; summarize candidate research questions (RQ1–RQ6). | 18/08/2026 |
| • Complete team task allocation; complete the project charter; discuss candidate research questions with the supervisor and determine the project direction according to supervisor guidance. | 25/08/2026 |
| • Finalize technical scope; select dataset(s), pose estimator(s), baseline model(s), and evaluation metrics; apply for/confirm required GPU resources. | 01/09/2026 |
| • Set up development environment; implement pose extraction/preprocessing pipeline; establish the initial baseline system. | 08/09/2026 |
| • Complete baseline implementation and preliminary evaluation; analyze failure cases; freeze the primary research question and innovation direction. | 15/09/2026 |
| • Design the proposed method, hypotheses, experimental controls, and ablation plan; begin implementation of the innovation. | 22/09/2026 |
| • Implement and debug the core innovation module; conduct initial experiments. | 29/09/2026 |
| • Integrate the proposed method with the full pipeline; perform initial baseline-versus-proposed comparison. | 06/10/2026 |
| • Refine the proposed method; conduct robustness/generalization experiments and preliminary ablation studies. | 13/10/2026 |
| • Conduct systematic quantitative experiments and controlled comparisons. | 20/10/2026 |
| • Complete ablation studies, failure-case analysis, qualitative visualization, and efficiency evaluation. | 27/10/2026 |
| • Finalize code and end-to-end demonstration; prepare figures, tables, and the first draft of the final report. | 03/11/2026 |
| • Complete the final report; produce the demonstration video and presentation; finalize project deliverables. | 10/11/2026 |

Team Member. Activity in which a team member plays a key role; Liang Hanzhang; Kolmakov Kirill; Teng Ziying; Shen Cong; Zhao Zhenning. Meeting Recording; C; R; I; I; I. Paper Review; C; I; A; I; R. Data Collection / Preparation; R; I; I; R; C. Coding; C; A; R; R; A. Experimental Evaluation; R; R; C; I; I. Final Report / Video; C; A; R; A; R. Summary Budget (if any):

- GPU computing resources for model training and evaluation if university resources are insufficient. - Additional storage for video datasets, extracted pose sequences, checkpoints, and experimental outputs if required. - AI coding monthly plan (e.g., Codex, Claude Code, DeepSeek). - No specialized hardware purchase is currently required.

Risk Assessment (if lab equipment is used):

- Person Identity and Ordering Instability In multi-person skeleton sequences, the ordering of Person 1 and Person 2 may not remain semantically consistent across samples or frames. Identity swaps or inconsistent ordering may undermine the proposed instance-preserving representation and make role-sensitive action recognition unreliable. Mitigation: inspect the NTU RGB+D 120 skeleton annotations before model development; define a deterministic person-ordering strategy or adopt a permutation-invariant representation; and explicitly evaluate the model’s sensitivity to identity swaps, including failure-case analysis. - Dataset Scope and Class Distribution The full NTU RGB+D 120 dataset contains many single-person or non-interaction actions, which may dilute improvements achieved specifically on two-person interaction classes. Some interaction classes may also have different sample distributions. Mitigation: use the two-person/mutual-interaction subset as the primary benchmark, preserve the official cross-subject and cross-setup splits, and report macro-F1 and per-class recall in addition to overall Top-1 accuracy. The full dataset may be used only as a supplementary evaluation where appropriate. - Confounding from Additional Model Capacity The proposed person-instance and relative-interaction branches may increase the number of trainable parameters. Any performance improvement could therefore be caused by increased model capacity rather than genuine preservation of person identity or interaction information. Mitigation: perform controlled ablation studies and include a parameter-matched baseline with comparable model capacity but without identity-specific features. Report model parameter count, computational cost and throughput alongside recognition performance. - Baseline Reproducibility and Software Compatibility The SkeletonX implementation relies on an older software environment and legacy dependencies, which may cause compatibility issues with current versions of Python, PyTorch and CUDA. Failure to reproduce the primary baseline could delay development of the proposed method. Mitigation: establish and document a reproducible environment during the initial project phase; validate the official baseline before modifying the architecture; and maintain PoseC3D or CTR-GCN as fallback baselines if SkeletonX cannot be reproduced within the planned setup period. - Computational Resource Limitation Multiple baseline, ablation and robustness experiments may require substantial GPU resources. Mitigation: use university GPU resources where available, use pretrained checkpoints where appropriate, and perform reduced-scale debugging before full training. - Research Scope and Schedule Risk Baseline reproduction, representation development, ablation studies and cross-dataset evaluation may exceed the available project duration. Mitigation: prioritize the instance-preserving representation and core NTU RGB+D 120 experiments; treat PKU-MMDv2 evaluation and additional modules as optional extensions.